## Potential Solution
Project Name: Interior Design by Harmony Date: 23 May, 2023
WBS Identifier # | Work Package | Internal Personal Required |  | External Personnel Required |  | Software and Tools |  | Supplies Required |  | Equipment Required |  | Furniture and Lighting |  | Other 2 | Start Date | Finish Date
|  | Name | Amount | Name | Amount | Name | Amount | Name | Amount | Name | Amount
1.1.1 | Project Plan | Project manager | 560 |  |  | Project management software | 200 | [7 empty] | 2023-04-01 | 2023-04-15
1.1.2 | Budget Plan | Project manager | 280 |  |  | Project management software | [8 empty] | 2023-04-08 | 2023-04-15
1.1.3 | Resource Plan | Project manager | 280 |  |  | Project management software | [8 empty] | 2023-04-08 | 2023-04-15
1.2.1 | Design Concept | Interior Designer | 6000 |  |  | Design Software - AutoCad | 1500 | Measuring tools | 50 | [5 empty] | 2023-04-15 | 2023-04-30
1.2.2 | Furniture and Materials Selection | Interior Designer | 1500 | [11 empty] | 2023-05-01 | 2023-05-31
1.2.3 | Lighting Plan | Interior Designer | 4500 |  |  | Design Software - AutoCad | [8 empty] | 2023-05-01 | 2023-05-15
1.3.1 | Furniture and Materials Purchasing | Purchasing | 200 | [8 empty] | Furniture and Lighting | 15000 |  | 2023-05-31 | 2023-06-05
1.3.2 | Installation | Assistant Designer | 800 | Contractors (painters, electricians) | 4000 | [9 empty] | 2023-06-20 | 2023-06-30
1.3.3 | Final Walkthrough | Assistant Designer | 200 |  |  |  |  | Camera | 500 | [5 empty] | 2023-06-30
Totals | 35570 | 14320 |  | 4000 |  | 1700 |  | 550 |  | 0 |  | 15000 |  | 0
Project Manager | $28/hr | 40 hours
Interior Design Lead | $100/hr | 120 hours
Assistant Designer | $20/hr | 50 hours
Purchasing | $20/hour | 10 hours

## Challenges
Step | Potential Challenges