## Communication Plan Template
Communications Plan for Project: Success Investor Day
Communications Item Forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format Medium (How) (Where) | Purpose (Why)
Twice weekly status meeting | Juan Cortez | Sandra Morgan Ramesh Patel Sophia Lamar Sarah Kim Priya Singh Michael Watson Valerie Shannon | 2x every week. Tuesday and Thursday 9 to 9:30am. Continuous. | Conference room A. In person and virtual. | Review schedule, scope, budget, venue, speakers, agenda, open issues/risks, road blocks.
Weekly project status report | Juan Cortez | All key stakeholders | Weekly by Friday at 10am. Continuous. | Email | Provide overview of key project status issues.
Change Control Board | Juan Cortez | Sandra Morgan All Success Inc. Department leads | Weekly 2 weeks on Monday at 10 to 10:30am. Continuous. | Conference room A. In person and virtual. | Review change requests. Approve or disapprove.
Sponsor 1:1 Meeting | Juan Cortez | Sandra Morgan | Weekly. Friday 9 to 9:30am. Continuous. | Virtual meeting | Update sponsor on status, blockers, risks.
Venue/Catering | Priya Singh | Sarah Kim Ramesh Patel Juan Cortez | Weekly. Monday 10 to10:30am. Continuous. | Virtual meeting | Search, issues and finalize venue and catering.
AV/IT Support | Sophia Lamar | Juan Cortez IT | Weekly. Monday 9 to 9:30am. Continuous. | Virtual meeting | Requirements, issues and finalize AV/IT.
Speakers/Agenda | Priya Singh | Valerie Shannon Juan Cortez | Weekly. Monday 9:30 to 10am. Continuous. | Virtual meeting | Search, issues and finalize speakers.
Version: 01 |  |  | Date: January 31