## Potential Solution
Resource Breakdown Structure/Resource Management Plan Project Name: Success Investor Day Date: January 31
WBS Identifier # | Work Package | Internal Personal Required |  | External Personnel Required |  | Software and Tools |  | Supplies Required |  | Equipment Required |  | Catering Day 1 |  | Catering Day 2 |  | Start Date | Finish Date
|  | Name | Amount | Name | Amount | Name | Amount | Name | Amount | Name | Amount | Name | Amount | Name | Amount
1.1.1 | Project Plan | PM | 13600 | [12 empty] | 2023-12-01 | 2023-12-30
|  | Intern | 1000
1.2.1 | Catering Plan | Catering | 750 | [8 empty] | Food+drinks | 2500 | Food+drinks | 20000 | 2023-01-15 | 2023-02-14
1.3.1 | AV and IT Plan | SME -IT/AV | 1000 | [6 empty] | AV per day | 600 |  |  |  |  | 2023-01-15 | 2023-02-07
1.4.1 | Venue Plan |  |  | Hotel Liaison | 10200 |  |  | Parking | 22500 | Venue | 8000 |  |  |  |  | 2023-01-15 | 2023-03-02
1.4.2 | Attendees Plan | Event Manager | 5100 |  |  |  |  | Onsite | 20250 | Virtual | 24750 |  |  |  |  | 2023-01-15 | 2023-03-02
1.4.3 | Speakers Plan | SME-Operations | 1815 | [6 empty] | Speaker | 2000 |  |  |  |  | 2023-01-15 | 2023-02-10
Totals | 134065 | 23265 |  | 10200 |  | 0 |  | 42750 |  | 35350 |  | 2500 |  | 20000
| per hour | hours/week | fixed hours | total hours
PM | 40 | 20 |  | 340
Sponsor | 30 |  |  | 0 | [6 empty] | Plus Contingency | 147471.5
Catering Manager | 25 |  | 30 | 30
SME - IT/AV | 40 |  | 25 | 25
Hotel Liaison | 30 | 20 |  | 340
Event Manager | 30 | 10 |  | 170
Intern | 25 |  | 40 | 40
SME - Operations | 55 | 1 | 16 | 33
Duration in weeks | 17

## Challenges
Step | Potential Challenges
2 | 10% increase in budget to offer all dietary restrictions
3 | support for streaming requirements
5 | low attendence due to flu and unfavorable economic conditions
6 | unable to find motivational speaker within budget and subject matter requirements