## Comm Mgt Plan Template
Communications plan template for project: AHI App
Communications item forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format medium (How) (Where) | Purpose (Why)
Twice weekly status meeting | Cary Manning | Priya Service Ram Samuels Oscar Money Keiko Tanaka Jose Garcia Cal Hamer | 2x every week. Tuesday and Thursday 9 to 9:30am. Continuous. | Conference room A. In person and virtual. | Review schedule, scope, budget, venue, speakers, agenda, open issues/risks, road blocks.
Weekly project status report | Cary Manning | All key stakeholders (IT, Finance, CEO, PO, Marketing, Contractors) | Weekly by Friday at 10am. Continuous. | Email | Provide overview of key project status issues.
Change Control Board | Cary Manning | All key stakeholders (IT, Finance, CEO, PO, Marketing, Contractors) | Weekly 2 weeks on Monday at 10 to 10:30am. Continuous. | Conference room A. In person and virtual. | Review change requests. Approve or disapprove.
Sponsor 1:1 Meeting | Cary Manning | Mary Smithers | Weekly. Friday 9 to 9:30am. Continuous. | Virtual meeting | Update sponsor on status, blockers, risks.
IT+Contractors | Priya Service | Cary Manning Keiko Tanaka Jose Garcia Cal Hamer Contractors | Weekly. Monday 10 to10:30am. Continuous. | Virtual meeting | Requirements, issues and finalize development.
Finance | Oscar Money | Cary Manning Mary Smithers | Weekly. Monday 9 to 9:30am. Continuous. | Virtual meeting | Requirements, issues and finalize finances and budget.
Version: 01 |  |  | Date: Jan 31