## Product Backlog
Product Backlog for AHI App
User Story Identifier | Priority | Category | Team | Role | Need | Value | Acceptance 1 | Acceptance 2 | Acceptance 3 | Acceptance 4 | Story Points | Comments
1 |  | Leadership | App v1 Dev | As leadership | I need access to data feeds from all sources | To save time and have read access to data | 1. access to data feeds | 2. includes all pertinent data sources | 3. realtime |  | 3 | Sprint 1
2 |  | Marketing | App v1 Dev | As marketing | I need on-demand reports | To automatically generate reports as needed | 1. automatically create report when requested | 2. contain pertinent information |  |  | 8 | Sprint 2
3 |  | Finance | App v1 Dev | As finance | I need secure order invoicing and processing | to protect private data and finance information | 1. password and 2FA access | 2. encryption on financal transactions |  |  | 5 | Sprint 3
4 |  | IT | App v1 Dev | As IT | I need App to interface with new hardware/software | to ensure smooth integrations with no delays | 1. design API to connect effortlessly | 2. automate testing with APIs |  |  | 5 | Sprint 4
5 |  | Customer | App v1 Dev | As customer | I need confirmation of all transactions | To get confidence in app | 1. provide receipt of transaction number and details | 2. order item, quantity and costs | 3. contact information |  | 2 | Sprint 5

## Product Backlog Example
Product Backlog for Project
User Story Identifier | Priority | Category | Team | Role | Need | Value | Acceptance 1 | Acceptance 2 | Acceptance 3 | Acceptance 4 | Acceptance 5 | Story Points | Comments
0001 | 1 | Customer | App Dev 1 | As a Coffee Shop Customer | I need easy access to order | To save time and reduce waiting | 1. Easy access to menu | 2. Pricing for all options | 3. Secure monetary transaction | 4. Order Confirmation |  | 5 | Sprint 1
0002 | 2 | Employee | App Dev 1 | As a store employee | I need real-time access to orders | So I can prepare in a timely manner | 1. Order information clearly displayed | 2. Customer's name | 3. Desired pick-up time | 4. Special instructions | 5. Label generation | 2 | Sprint 1

## Story Points
1 Story Point | 2 Story Points | 3 Story Points | 5 Story Points | 8 Story Points
total story points = 2 + 3 + 5 + 5 + 2 = 17
Less Complex More Complex
User Story 1
User Story 2
User Story 3
User Story 4
User Story 5

## Story Points Solution
1 Story Point | 2 Story Points | 3 Story Points | 5 Story Points | 8 Story Points
Total Story Points: 1 + 2 + 3 + 3 + 5 = 14
Less Complex More Complex
User Story 1
User Story 2
User Story 3
User Story 4
User Story 5