## Risk Register Template
Project: AHI App Date: Jan 31
# | Cause (condition/situation) | Event | Impact | Risk owner | Category | Probability risk rating | Impact risk rating | Risk score | Trigger | Response
1 | Scope creep | Overbudget | Reduce ROI | Oscar Money | Threat | 4 | 3 | 12 | More tasks and requirements added | Re-assess scope and project goals
2 | Design flaws | Delay in launch | Delay in benefits | Cal Hamer | Threat | 4 | 5 | 20 | Poor beta testing and feedback | Add more frequent feedbacks with customer and marketing
3 | Development delays | Delay in launch | Delay in benefits | Cal Hamer | Threat | 4 | 5 | 20 | Missed deadlines and milestones | Re-assess timelines and manpower needed.
4 | IT capability issues | Delay in launch | Delay in benefits and reduce in ROI | Priya Service | Threat | 4 | 2 | 8 | Backend infrastructure inadequate for needed load, high latency, low performance | Re-assess infrastructure needs
5 | Internal app development capacity | Delay in launch | Delay in benefits and reduce in ROI | Ram Samuels | Threat | 4 | 2 | 8 | Missed deadlines and milestones | Re-assess requirements and manpower and timelines needed.
6 | Poor customer acceptance | Low useage by customers | Reduced customer satisfaction | Mary Smithers | Threat | 3 | 5 | 15 | Low downloads of app | Re-assess customer need from VoC
7 | Management support | Increased motivation and dedication | Greater chance of success, launching on time and within budget | Mary Lin | Opportunity | 5 | -5 | -25 | Good project statuses | Company rewards and bonus
Total Risk Score | [7 empty] | 58 | Risk Exposure
|  | Probability risk rating |  | Impact risk rating
|  | 5: High |  | 5: High
|  | 4: High to moderate |  | 4: High to moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to low |  | 2: Moderate to low
|  | 1: Low |  | 1: Low