## Blank
Sprint Backlog for Project:
Story ID | Resource | Story/Task | Time Required | Time Remaining
1 Leadership needs access to data feeds from all sources | Lead: Cal | User Story: Access to data feeds from all sources | 28
| Abe | Task 1: Identify data sources | 4
| Bob | Task 2: Work out API for each source | 8
| Cory | Task 3: Gain access to each source | 8
| Dale | Task 4: Confirm data accessed is required and in realtime | 8
Task 5
2 Marketing needs on-demand reports | Lead: Ram | User Story: On-demand reports | 48
| Abe | Task 1: Design format of report | 16
| Bob | Task 2: Access data and populate report | 24
| Cory | Task 3: Export report | 8
Task 4
Task 5
3 Finance needs secure ordering invoicing and processing | Lead: Oscar | User Story: Secure ordering invoicing and processing | 32
| Abe | Task 1: Implement password and 2FA | 16
| Bob | Task 2: Add encryption on financial transactions | 16
Task 3
Task 4
Task 5
4 IT needs App to interface with new hardware/software | Lead: Priya | User Story: interface with new hardware/software | 32
| Abe | Task 1: design API to connect | 16
| Bob | Task 2 automate testing with API | 16
Task 3
Task 4
Task 5
5 Customer needs confirmation of transaction | Lead: Cal | User Story: confirmation of transaction | 24
| Abe | Task 1: design receipt layout | 8
| Bob | Task 2: extract order item, quantity and costs for receipt | 8
| Cory | Task 3: create receipt | 8
Task 4
Task 5
Total Sprint Hours |  |  | 164 | 0

## Example
Sprint Backlog for Project: Coffee Shop App
Story ID | Resource | Story/Task | Time Required (Hours) | Time Remaining (Hours)
0001 Customer Needs 1 | Lead: Ram | User Story: Easy Access to Orders | 77
| Marvin | Task 1: Develop visible drop-down menu | 20
| Marvin | Task 2: List easy to view pricing for all menu options | 15
| Don | Task 3: Develop secure payment transaction feature | 30
| Mona | Task 4: Develop order confirmation acknowledgement function | 12
Task 5
0002 Employee Needs 1 | Lead: Sally | User Story: Real-Time Access to Orders | 30
| Kyoko | Task 1: Develop visual order confirmation screen | 10
| Priya | Task 2: Program capability to see customer's name | 5
| Priya | Task 3: Clearly display order pick-up time | 5
| Harold | Task 4: List any applicable special instructions | 5
| Harold | Task 5: Automatically generate label when order is complete | 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
Total Sprint Hours |  |  | 107 | 0