## SWOT Worksheet
SWOT Worksheet
Strengths (Cause) | Opportunities (Event)
Teamwork | Teambuilding with current and new employees
Give back to community | Better reputation of company and products with community
Clean up environment | Seen by community as committed to environmental causes
Opportunities for sales | Marketing and revenue from product sales
CEO support | Engage employees
Weaknesses (Cause) | Threats (Event)
Bad weather | Rain impacts event negatively
Injury from hike | Liability since it’s a company event
Traffic | Employee injury and liability
Transportation | Delays
Catering | Food contamination and allergies
Not enough volunteers | Cannot participate in event

## Risk Register Template
Project: ORI Magic Mountain Cleanup Date: Feb 15
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
1 | Teamwork | Teambuilding with current and new employees | Better collaboration and cooperation | PM | Opportunity | 4 | -4 | -16 | None | Plan for more teambuilding events
2 | Give back to community | Better reputation of company and products with community | Better public view of company | Public Relations | Opportunity | 3 | -4 | -12 | None | Add this event to company website and publish in social media
3 | Clean up environment | Seen by community as committed to environmental causes | Better public view of company | Public Relations | Opportunity | 5 | -5 | -25 | None | Add this event to company website and publish in social media
4 | Opportunities for sales | Marketing and revenue from product sales | Better sales | Marketing | Opportunity | 4 | -5 | -20 | More sales, hits to website, social media | Prepare for bigger load on websites and responses to social media
5 | CEO support | Engage employees | Better morale | CEO | Opportunity | 3 | -5 | -15 | None | More committed employees
6 | Bad weather | Rain impacts event negatively | Poor public view of company | Environmental | Threat | 2 | 4 | 8 | Weather reports | Prepare to cancel if weather too severe
7 | Injury from hike | Liability since it’s a company event | Injury risk | Healthy and safety | Threat | 3 | 1 | 3 | Remind employees to be careful | Prepare first aid kits
8 | Traffic accident | Employee injury and liability | Injury risk | Healthy and safety | Threat | 3 | 1 | 3 | Bus got into accident | Hire qualified bus drivers
9 | Transportation | Delays | Poor public view of company | Public Relations | Threat | 3 | 3 | 9 | Traffic reports | Leave early
10 | Catering | Food contamination and allergies | Poor public view of company | Public Relations | Threat | 3 | 3 | 9 | People start getting sick | Hire qualified caterers
11 | Not enough volunteers | Cannot participate in event | Poor engagement by employees in company events | CEO | Threat | 1 | 5 | 5 | Lack of volunteers by deadline | CEO encourage volunteers, offer incentives
Total Risk Score | [7 empty] | -51
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low

## Risk Matrix Threats
Project: ORI Magic Mountain Cleanup
P | 5 | [5 empty] | Top Risks
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 | [5 empty] | R1 | Bad weather | Rain impacts event negatively | Poor public view of company | Prepare to cancel if weather too severe
B | [6 empty] | R2 | Injury from hike | Liability since it’s a company event | Injury risk | Prepare first aid kits
A | 3 | R2, R3 |  | R4, R5 |  |  | R3 | Traffic accident | Employee injury and liability | Injury risk | Hire qualified bus drivers
B | [6 empty] | R4 | Transportation | Delays | Poor public view of company | Leave early
I | 2 |  |  |  | R1 |  | R5 | Catering | Food contamination and allergies | Poor public view of company | Hire qualified caterers
L | [6 empty] | R6 | Not enough volunteers | Cannot participate in event | Poor engagement by employees in company events | CEO encourage volunteers, offer incentives
I | 1 |  |  |  |  | R6 | R7
T | [6 empty] | R8
Y |  | 1 | 2 | 3 | 4 | 5
Scoring
| I | M | P | A | C | T | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
[7 empty] | Urgent List High |  | 15-25

## Risk Matrix Opp
Project: ORI Magic Mountain Cleanup
P | 5 |  |  |  |  | R3 | Top Opportunities
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 |  |  |  | R1 | R4 | R1 | Teamwork | Teambuilding with current and new employees | Better collaboration and cooperation | Plan for more teambuilding events
B | [6 empty] | R2 | Give back to community | Better reputation of company and products with community | Better public view of company | Add this event to company website and publish in social media
A | 3 |  |  |  | R2 | R5 | R3 | Clean up environment | Seen by community as committed to environmental causes | Better public view of company | Add this event to company website and publish in social media
B | [6 empty] | R4 | Opportunities for sales | Marketing and revenue from product sales | Better sales | Prepare for bigger load on websites and responses to social media
I | 2 | [5 empty] | R5 | CEO support | Engage employees | Better morale | More committed employees
L | [6 empty] | R6
I | 1
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25