## WBS Template
|  | 1.0 New Hire Orientation Project |  | Level 1 Project Level
1.1 Plan Project | 2.1 Execute Project |  | 3.1 Close Project | Level 2 Phase Level
1.1.1 Develop project goals and objectives | 2.1.1 Secure and prepare venue |  | 3.1.1 Solicit feedback from participants | Level 3 Work Package Level
1.1.2 Develop agenda and plans for each event | 2.1.2 Implement A/V plan |  | 3.1.2 Close events
1.1.3 Develop catering plan | 2.1.3 Implement catering plan |  | 3.1.3 Close venue
1.1.4 Managing speakers and activities | 2.1.4 Prepare speakers and materials |  | 3.1.4 Conduct retrospectives and lessons learned
1.1.5 Develop A/V plan | 2.1.5 Implement agenda and activities for each event
1.1.6 Get approval