## Blank
Resource Breakdown Structure Project Name: New Hire Orientation Project Date: Feb 15
WBS Identifier # | Work Package | Internal Personal Required | External Personnel Required | Venue Costs | Materials Required | Supplies Required | Equipment Required | Comments | Total Direct Costs
1.1.1 | Develop project goals and objectives
1.1.2 | Develop agenda and plans for each event
1.1.3 | Develop catering plan
1.1.4 | Managing speakers and activities
1.1.5 | Develop A/V plan
1.1.6 | Get approval | 11130 | [5 empty] | direct costs from 60% total personnel costs | 11130
2.1.1 | Secure and prepare venue | [6 empty] | free, covered by company
2.1.2 | Implement A/V plan | [5 empty] | 200
2.1.3 | Implement catering plan |  |  | 400 |  |  |  | breakfast + lunch for 20
2.1.4 | Prepare speakers and materials
2.1.5 | Implement agenda and activities for each event | 3710 |  |  | 600 |  | 24000 | marketing materials cost and IT costs | 3710
3.1.1 | Solicit feedback from participants
3.1.2 | Close events
3.1.3 | Close venue
3.1.4 | Conduct retrospectives and lessons learned | 3710 | [5 empty] | direct costs from 20% total personnel costs | 3710
TOTAL COSTS |  | 18550 | 0 | 400 | 600 | 0 | 24200 | 0 | 18550
Contingency Requirements (10%) | [8 empty] | 1855
Personnel Cost Requirements | [5 empty] | Note: Update Cost Categories to reflect actual project requirements
Rate | Name | Hours | Costs
50 | Hiroshi Tanaka (IT) | 20 | 1000
50 | Ursula Miller (Finance) | 2 | 100
50 | Priya Sanders (Marketing) | 25 | 1250
50 | Sam Manning (Facilities) | 10 | 500
50 | Sunny Marsh (HR) | 3 | 150
50 | Ram Finland (HR) | 3 | 150
50 | Gloria Fisher | 280 | 14000
50 | Marcus Wilson | 28 | 1400
TOTAL |  |  | 18550

## Demo Example
Resource Breakdown Structure: "Hierarchical breakout of resources by category and type" Project Name: Annual Executive Meeting Support Project Date: 30 April 20XX
WBS Identifier # | Work Package | Personnel Costs | Beverage Costs | Catering Costs | Support Costs | Venue Support | Comments | Total Direct Costs
1.1.1 | Define Venue |  |  |  |  | 1000 | Initial Deposit | 1000
1.1.2 | Determine Attendees |  |  |  | 1500 |  | Handouts/Print | 1500
1.1.3 | Plan Team | [6 empty] | 0
1.1.4 | Plan Beverages |  | 500 |  |  |  | Coffee/Juice | 500
1.1.5 | Plan Catering |  |  | 1000 |  |  | Box Lunches | 1000
2.1.1 | Assemble Packages | [6 empty] | 0
2.1.2 | Install AV | [6 empty] | 0
2.1.3 | Set Up Venue | [6 empty] | 0
2.1.4 | Conduct Meet |  |  |  | 1000 |  | AV/IT Support | 1000
3.1.1 | Close Out Venue | 600 |  |  |  | 1000 | Clean/Venue $ | 1600
3.1.2 | Prepare Final Reports | [6 empty] | 0
3.1.3 | Pay Outstanding Invoices | 30 |  |  |  |  | Bookkeeper | 30
3.1.4 | Perform Lessons Learned | [6 empty] | 0
TOTAL COSTS |  | 630 | 500 | 1000 | 2500 | 2000 | 0 | 6630
Contingency Requirements (10%) | [7 empty] | 663